## Start here
DARIL™
RAID LOG TEMPLATE
A clean, ready-to-use RAID log: the four registers every project keeps alongside the plan — Risks, Assumptions, Issues and Dependencies. Fill in the tabs below. Each has the columns that matter, dropdowns where they help, and two sample rows so you can see the shape of a real entry.
WHAT RAID STANDS FOR
Two readings are common: Risks, Assumptions, Issues, Dependencies (used here) — or Risks, Actions, Issues, Decisions. Neither is wrong. Pick one, define each term, and hold the team to it.
HOW TO USE IT
Risks | what could go wrong — scored before it bites.
Assumptions | what you're relying on — each with a date to validate it.
Issues | what's going wrong now — owned, with an action and target.
Dependencies | what you owe and are owed — inbound or outbound.
Give every item one named owner, review the log on a fixed cadence, and mark items closed rather than deleting them — that record is where your lessons come from.
BEYOND RAID
A RAID log stops at four registers. DARIL the app extends them into a full system of record — Deliverables, Actions, Risks, Issues, Lessons, plus Decisions, Gates and Backlog — with the connections between items kept intact, in one offline file. See darilpm.com.
Visit darilpm.com →
Free template · v2 · 2026 · darilpm.com — share it freely.

## Risks
RISKS — what could go wrong
ID | Risk | Owner | Probability (1-5) | Impact (1-5) | Score | Response | Status
R-014 | Third-party KYC vendor may not certify before the release gate | A. Okafor | 3 | 4 | 12 | Mitigate — start certification 6 weeks early; line up fallback vendor | Open
R-021 | Peak-load testing slips into the freeze window | J. Reyes | 2 | 4 | 8 | Monitor; pre-book the test environment | Monitoring

## Assumptions
ASSUMPTIONS — what you're relying on
ID | Assumption | Owner | Validated? | Validate by | Status
A-007 | Existing customer auth service can handle the new SSO flow without rework | P. Nair | No | End of discovery | Open
A-011 | Compliance sign-off needed only once, at the release gate | A. Okafor | Partially | Gate 2 | Open

## Issues
ISSUES — what's going wrong now
ID | Issue | Owner | Severity | Raised | Action & target | Status
I-009 | Staging environment unavailable, blocking integration testing | J. Reyes | High | 12 Mar | Platform team rebuilding env — target 18 Mar | Open
I-012 | Two conflicting requirements for transaction limits | P. Nair | Medium | 14 Mar | Decision needed from product — target 19 Mar | In progress

## Dependencies
DEPENDENCIES — what you owe and are owed
ID | Dependency | Direction | With | Needed by | Status
D-003 | Final fraud-rules spec from the risk team | Inbound | Fraud & Risk | Start of build | At risk
D-005 | API contract delivered to the partner integration team | Outbound | Partner Eng | Gate 2 | On track