## Start here
DARIL™ Risk Register
Likelihood × Impact → Severity, with pre- and post-mitigation. The risk register from the DARIL method.
HOW TO USE
1. Go to the Risk Register tab. Keep one register per project.
2. Log each risk in its own row. Give it an ID and the date you raised it.
3. Set Pre-Mitigation Likelihood and Impact (Low / Med / High). Severity fills in automatically.
4. Name one owner and write the mitigating action you'll take.
5. Set Post-Mitigation Likelihood and Impact — the residual risk once the action is in place.
6. Review on a fixed cadence. A risk register only earns its keep if it's a living record.
THE SEVERITY SCALE
Impact →
Likelihood ↓ | Low | Med | High
High | Medium | High | High
Med | Low | Medium | High
Low | Low | Low | Medium
Rows = Likelihood, columns = Impact. Green = Low, amber = Medium, red = High severity.
Built with DARIL — the system of record for complex projects → darilpm.com
DARIL™ · risk-register-template · v1

## Risk Register
ID | Date raised | Risk description | Pre-Mitigation |  |  | Owner | Mitigating action | Post-Mitigation
|  |  | Likelihood | Impact | Severity |  |  | Likelihood | Impact | Severity
R-014 | 2026-01-08 | Third-party KYC vendor may not certify before the release gate | Med | High | High | A. Okafor | Start certification 6 weeks early; line up a fallback vendor | Low | High | Medium
R-021 | 2026-01-15 | Peak-load testing slips into the change-freeze window | Low | High | Medium | J. Reyes | Pre-book the performance environment; reserve the test slot before freeze | Low | Med | Low
R-027 | 2026-01-22 | New biometric login fails the accessibility review | Med | Med | Medium | P. Andersson | Run an accessibility audit in beta; keep the PIN fallback | Low | Med | Low
R-033 | 2026-02-03 | App-store review rejects the release over a privacy-manifest change | Med | High | High | A. Okafor | Pre-submit for review; prepare an expedited-review request | Low | High | Medium
R-038 | 2026-02-10 | Core-banking API rate limits throttle launch-day traffic | High | High | High | J. Reyes | Negotiate a higher quota; add client-side backoff and caching | Med | High | High